# Adoration Chapel for St Angela Merici Church

## Initiation Plan

27 June 2008

Dave & Kathy Engels

714-992-1306

engelsda@sbcglobal.net

### Step by Step Actions To Get Things Going

- Pastor authorization to begin-

- Form ‘Core’ Group

- Order ‘Starter Kits’ from Missionaries of Blessed Sacrament-

- Pastor & Adoration Chapel Core Group meet to review plan-

- Pastor informs Parish Council and urges cooperation-

- Bulletin Notifications about Adoration Chapel-

- Parish Priests/Deacon  homilies address the blessings that come from Perpetual Adoration-

- Core Group formulates contact plan to enlist support from parish ministries-

- Letter from pastor (Core writes, Core Group approves & forwards to Pastor (edits,approves & signs) , Core distributes to parish ministries asking for their support for Adoration chapel-

- Various people selected to address  parish ministries & urge  signups for adoration times. Coordination meeting with these people-

- Parish Ministries are addressed & signups requested-

- Pastor, priests, deacons, addresses congregation at each Mass. Discusses ‘why’ Adoration, and urges signups. Signup sheets & pencils in pews for each Mass, collected at end of Mass & new sheets & pencils put out for next Mass. Ushers instructed about distributions & collections-

- 2-3 people appointed & set up Adoration chapel Data Base-

- Adoration Chapel Data base activated-names from Priest Promoter weekend collected, put into data base

- Telephone Committee formed to call signups & verify interest and availability for particular hour & day-

- Note: It took St Dorothy’s 6 weeks after “Adoration Chapel” homily weekend to assemble required number of adorer/guardians and get organized.

- Pastor authorizes modifications to room for Adoration Chapel. Modifications begin. Allocate 4 weeks for modifications to be completed-  .

- Coordinator, Division Leaders, Hourly Captains appointed

19. The Hourly Captains call each adorer/guardian on their list and tell them

- Starting Date

- Location of the Chapel

- Parking Arrangements

- Location of the restroom

- Security Arrangements

- Location and use of telephones

- Names of Adorer/guardians before and after them

- How to obtain a substitute

- Name and Phone number of Hourly Captain and Division Leader

19. Petition Book, Hourly Signup Book, Religious Materials procured & prepared –

- When sufficient number of signups are received and staffing is complete:

For the first 2-3 weeks, the 24 coordinators call their adorer/guardians to remind them of their commitment and get heads up on any upcoming absences

- Thank them for wanting to spend an hour with Jesus each week

- Confirm the day and hour requested and ask whether they would be willing to take an hour that is opened.

- Be encouraging and supportive. Share with them the many blessings that come from their holy hour; they will look forward to coming each week.

- If there is a need, ask if they would like to be an hourly captain and/or if the would be willing to take more than one holy hour a week

- Record their address/phone/email so a mailing list can be compiled

- Pastor sends each adorer/guardian an acknowledgement letter –  Core writes, Pastor edits/approves/signs.  Core  handles mailing-

22. The Hourly Captains call each adorer/guardian on their list and tell them:

- Starting Date

- Location of the Chapel

- Parking Arrangements

- Location of the restroom

- Security Arrangements

- Location and use of telephones

- Names of Adorer/guardians before and after them

- How to obtain a substitute

- Name and Phone number of Hourly Captain and Division Leader

23.  Materials needed to start Perpetual Eucharistic Adoration:

- Pamphlets, prayer cards, posters

- Inspirational materials

- Reasons for Perpetual Eucharistic Adoration

- Bulletin Announcements

- Perpetual Adoration Invitation with Q&A section

- Answers to Commonly Asked Questions

- Coordinator Instructions

- Division Leader Chart

- Hourly Captain Chart

10.Daily Schedule Layout

11.Practical tips for substitutes

12. Testimony of Favors Granted

13.Place Perpetual Eucharistic Adoration Posters in neighboring parishes ( only with pastors permission)

  - Newsletter from Missionaries of Blessed Sacrament.

  - Sign In Sheets

  - Petition Book

  - Contact Information for substitutes, Division Leaders & Daily Captains

- Prepare Perpetual Adoration Substitute List- those willing to fill in if a committed adorer/guardian can’t make their allotted time.

- A few people committed to cleaning the chapel once/week or as necessary & refurbish supply of religious materials-pamphlets,holy cards, prayer sheets, etc.

- Full time Perpetual Adoration   starts:  Pastor & priests formally bless the chapel and begin Adoration

- Adoration Chapel Committee designated by Pastor

- Adoration Chapel Committee  meets once/month for action items, statussing, resolution of any problems